## Matlab_Simulink
Basic training plan for newcomer
|  |  | Duration | 200 | hours
No | ID | Item | Detail | Description | Training Method | Mentor | Status | Duration | Acttual Effort | Time |  | Planned Start Date | Actual Trainning Date | Reference | Evaluating Result(%)
1 | MBD_001 | A_Introduction MATLAB - SIMULINK | 01_Intro_MATLAB_part1_01.06.pptx 02_Intro_Simulink_part2_01.05.pptx | - MATLAB Introduction - Vectors and arrays - MATLAB Operation - M-script programming - Simulink introduction - Model standard (JMAAB) - Introduction to Model Verification | Lecture | NHTinh | Completed | 3.5 | 3.5 | 8:30 | 12:00 | 2018-03-01 |  | A_intro | 90%
[5 empty] | Exercise and Solution | NHTinh | Completed | 4.5 | 4.5 | 13:30 | 18:00 | 2018-03-01
2 | MBD_002 | B_Model Implementation | 01_Model_Implemented_from_Code_v01.ppt | - General concept - Procedure reversing C - Syntax-C compare to model - Create model from specification - Set up for model to auto-code | Lecture | NHTinh | Completed | 3.5 | 4 | 8:30 | 12:00 | 2018-03-02 |  | B_Model_Implement | 90%
[5 empty] | Exercise and Solution | NHTinh | Completed | 12.5 | 16 | 8:30 | 18:00 | 2018-03-02
3 | MBD_003 | C_Stateflow | Simulink_Stateflow_Chart_rev_00_04.ppt | - Explain Simulink stateflow chart advantage. - Understand Simulink stateflow chart user interface. - Explain stateflow chart hierarchy. - Use correct transition for creating stateflow chart. - Create input test signal for debugging the chart. - Create stateflow chart from given specification. - Describe flowchart and coding relation. | Lecture | NHTinh | Completed | 3.5 | 3 | 8:30 | 12:00 | 2018-03-05 |  | C_StateFlow | 85%
[5 empty] | Exercise and Solution | NHTinh | Completed | 4.5 | 5 | 13:30 | 18:00 | 2018-03-05
4 | MBD_004 | D_Verification | Model_MCDC_Coverage_rev_02_00_trne.pptx |  | Lecture | NHTinh | Completed | 3.5 | 4 | 8:30 | 12:00 | 2018-03-06 |  | D_Model_Verification | 85%
[5 empty] | Exercise and Solution | NHTinh | Completed | 12.5 | 16 | 8:30 | 18:00 | 2018-03-06
5 | MBD_005 | E_Skill_up_model | 02_Back_to_Back_verification_02.ppt Quick_GL_for_UT_Hand_Code_Supplement.xlsx | - Introduction - Parts of Back-to-Back Verification Model - Back-to-Back Verification Model | Exercise and Solution | NHTinh | Completed | 20.5 | 24 | 8:30 | 18:00 | 2018-03-08 |  | E_Skill_up_model | 85%
6 | MBD_006 | Solutions_output | Solution_DoorUnlock_workshop_v01.pptx | - DoorUnlock_workshop | Lecture | NHTinh | Completed | 3.5 | 4 | 0.35417 | 0.5
[5 empty] | Exercise and Solution | NHTinh | Completed | 12.5 | 16 | 0.35417 | 0.75
7 | MBD_007 | Trial MBD | 09_FromCustomer\トライアル問題\課題説明資料\トライアル１－課題パート.pptx | Step 1 | try_a (1h) try_b (2h) try_c (3h) try_d (2h) | HDHieu | On-going | 24 | 30 | 8:30 | 18:00 | 2018-04-09
|  |  |  | Step 2 | try_a (1h) try_b (2h) try_c (3h) try_d (2h) | NHTinh | On-going | 16 | 10 | 8:30 | 18:00 | 2018-04-12
|  |  |  | Step 3 | try_a (3.5h) try_b (4.5h) try_c (19.5h) try_d (4.5h) | VXTung | New | 40 |  | 8:30 | 18:00 | 2018-04-16
|  |  |  | Step 4A | Create test case (40.5) try_a (3.5h) try_b (12.5h) try_c (16h) try_d (0.5h) Verify model (3.5) try_a (0.5h) try_b (0.5h) try_c (2h) try_d (0.5h) | NHTinh | New | 32 |  | 8:30 | 18:00 | 2018-04-23
|  |  |  | Step 4B | try_a (0.5h) try_b (0.5h) try_c (2h) try_d (0.5h) | NHTinh | New | 3.5 |  | 8:30 | 12:00 | 2018-04-27
|  |  |  | Step 5 | Report | NHTinh | New | 4.5 |  | 13:30 | 16:00 | 2018-04-27